## Summary
This information is from: |  | Patrick Dolan
Date: | 2004-03-29
Business Unit | Service, Program Project | Item | Priority 1, 2 or 3 | Business Drivers | Vendor | Cost per Item | Quantity | Total Cost | Start Date Month/ Year | Payment Schedule | Operating or Capital | Expense Class | Hardware Replacement Date | Cost Center | What alternatives were considered? | What if we don't purchase? | Assumptions | Comments | Data Source | Data Date
Enter data below this row
| Clin Doc | Software |  |  | Cerner |  |  |  | 2004-06-01 |  | Capital
|  | Vendor Software |  |  |  | 0 | 1 | 0 |  |  | Capital
|  | Other Software |  |  |  | 0 | 1 | 0 |  |  | Capital
|  | Hardware | [8 empty] | Capital
|  | Vendor Hardware |  |  |  | 0 | 1 | 0 |  |  | Capital
|  | Other Hardware |  |  |  | 0 | 1 | 0 |  |  | Capital
|  | Implementation | [8 empty] | Capital
|  | Children's Labor |  |  |  | 334700 | 1 | 334700 |  |  | Capital
|  | Vendor Labor |  |  |  | 0 | 1 | 0 |  |  | Capital
|  | Contractor Labor |  |  |  | 0 | 1 | 0 |  |  | Capital
|  | Vendor Travel |  |  |  | 0 | 1 | 0 |  |  | Capital
|  | Children's Travel |  |  |  | 0 | 1 | 0 |  |  | Capital
|  | Contractor Travel |  |  |  | 0 | 1 | 0 |  |  | Capital
|  | Children's Comm/CM |  |  |  | 0 | 1 | 0 |  |  | Capital
|  | Children's Training |  |  |  | 0 | 1 | 0 |  |  | Capital
|  | Maintenance | [8 empty] | Operating
|  | Vendor Maintenance |  |  |  | 0 | 1 | 0 |  | annual | Operating
|  | Other Maintenance |  |  |  | 0 | 1 | 0 |  |  | Operating
|  | Operating Labor |  |  |  | 334700 | 1 | 334700 |  |  | Operating
|  | Capital Costs | [5 empty] | 334700
|  | Operating Costs | [5 empty] | 334700
|  | Total Project Costs | [5 empty] | 669400
|  | FY04 | FY05 | FY06 | FY07
| Software | 0 | 0 | 0 | 0 | 0
| Hardware | 0 | 0 | 0 | 0 | 0
Implementation
| Company Labor | 46150 | 288550 | 0 | 0 | 334700
| Vendor Labor | 0 | 0 | 0 | 0 | 0
| Contractor Labor | 0 | 0 | 0 | 0 | 0
| Children's Other | 0 | 0 | 0 |  | 0
| Vendor Other | 0 | 0 | 0 |  | 0
| Contractor Other | 0 | 0 | 0 |  | 0
| Impl Total | 46150 | 288550 | 0 | 0 | 334700
| Total | 46150 | 288550 | 0 | 0 | 334700 | Capital Costs Only
| Current balance in CIS phase III fund | 2200000
| Minus projected FY04 spend | 46150
| Remaining budget for FY2005 | 2153850
| FY05 projected spend | 288550
| Minus FY05 balance | 2153850
| Unfunded FY2005 | -1865300
| Unfunded FY2006 | 0
| ADDITIONAL FUNDING | -1865300

## Company Labor
| Project Name | [8 empty] | Project Manager
|  |  | 2004 | [5 empty] | 2005 | [11 empty] | Hours
Roles |  |  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Hourly Estimates |  |  | Plan | Define | Design | Build Test | Build Test | Build Test | Build Test | Build Test | Build Test | Build Test | Deploy | Build Test | Deploy | Close | Close | Close
O | Application Analysts | [19 empty] | 0
O | Business Analysts |  | 4 | 54 | 246 | 170 | 190 | 194 | 252 | 215 | 123 | 260 | 540 | 44 | 64 | 9 | 3 |  |  |  | 2368
O | Project Manager |  | 100 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 160 | 9 | 0 |  |  |  | 2029
O | Communications Specialist | [19 empty] | 0
C | Technical PM | [19 empty] | 0
O | Trainers |  | 2005 May: 24 | 24
O | Systems Administrator |  | 2004 Sep: 2; 2004 Dec: 1; 2005 Feb: 28 | 31
O | UNIX-BMC | [19 empty] | 0
O | Citrix | [19 empty] | 0
O | Network Engineer |  | 2004 Aug: 4; 2004 Sep: 27; 2004 Oct: 5 | 36
O | Interface Engineer |  | 2004 Jul: 1; 2005 Jan: 26; 2005 Feb: 174; 2005 Mar: 174; 2005 Apr: 130 | 505
O | DBA |  | 2004 Aug: 3; 2004 Sep: 3; 2004 Oct: 25; 2004 Nov: 6 | 37
O | Production Support Analyst | [19 empty] | 0
O | Director |  | 3 | 12 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 8 | 4 | 3 |  |  |  | 70
O | Business Sponsors |  | 6 | 32 | 60 | 24 | 16 | 50 | 12 | 10 | 10 | 16 | 10 | 12 | 16 | 16 | 2 |  |  |  | 292
O | Vendor |  | 2004 Jul: 1; 2004 Sep: 13; 2004 Oct: 8; 2004 Dec: 57; 2005 Jan: 30; 2005 Feb: 199; 2005 Mar: 110; 2005 May: 16 | 434
| Total Hours |  | 115 | 265 | 515 | 396 | 376 | 466 | 484 | 790 | 581 | 570 | 754 | 220 | 248 | 38 | 8 | 0 | 0 | 0 | 5826
|  |  | 2004 Jul: 2004; 2005 Jan: 2005 | Cost
Childrens Resources | Cost Estimates | Rate | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
O | Application Analysts | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
O | Business Analysts | 50 | 200 | 2700 | 12300 | 8500 | 9500 | 9700 | 12600 | 10750 | 6150 | 13000 | 27000 | 2200 | 3200 | 450 | 150 | 0 | 0 | 0 | 118400
O | Project Manager | 50 | 5000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 8000 | 450 | 0 | 0 | 0 | 0 | 101450
O | Communications Specialist | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | Technical PM | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
O | Trainers | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200
O | Systems Adminiatrator | 50 | 0 | 0 | 100 | 0 | 0 | 50 | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550
O | UNIX-BMC | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
O | Citrix | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
O | Network Engineer | 50 | 0 | 200 | 1350 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800
O | Interface Engineer | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 1300 | 8700 | 8700 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25250
O | DBA | 50 | 0 | 150 | 150 | 1250 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1850
O | Production Support Analyst | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
O | Director | 50 | 150 | 600 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 200 | 400 | 200 | 150 | 0 | 0 | 0 | 3500
O | Governance | 50 | 300 | 1600 | 3000 | 1200 | 800 | 2500 | 600 | 500 | 500 | 800 | 500 | 600 | 800 | 800 | 100 | 0 | 0 | 0 | 14600
O | Vendor | 150 | 150 | 0 | 1950 | 1200 | 0 | 8550 | 4500 | 29850 | 16500 | 0 | 2400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65100
| Total Labor |  | 5850 | 13250 | 27050 | 20600 | 18800 | 29000 | 27200 | 59400 | 40050 | 28500 | 39300 | 11000 | 12400 | 1900 | 400 | 0 | 0 | 0 | 334700
| Fiscal Year 2004 Total | 46150
| Fiscal Year 2005 Total | 288550
| Fiscal Year 2006 Total | 0
| TOTAL | 334700
| Labor SUBTOTAL | 334700
Travel SUBTOTAL
Change Mgmt/Comm
Training
| Implementation Total | 334700
| Operating Labor | 334700
| Labor Rate | 50
104000
8666.6667

## Vendor Labor
Project X Hours |  |  | 2004 | [22 empty] | 2006
Role | Resources |  | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
Phase |  |  |  |  | Plan/Define | Plan/Define | Plan/Define | Design | Design | Design | Design | Design | Design | Design | Design | Build | Build | Build | Build | Test | Test | Test | Test | Pilot | Impl | Impl | Impl | Maintain | Maintain
PD | Partner/Project Director | [36 empty] | 0
PE | Project Executive | [36 empty] | 0
PA | Project Architect | [36 empty] | 0
PA | Project Architect | [36 empty] | 0
TPM | Technical PM | [36 empty] | 0
SE | Systems Engineer | [36 empty] | 0
TA | Technical Engineer | [36 empty] | 0
AS | Application Specialist | [36 empty] | 0
LC | Learning Consultant | [36 empty] | 0
SC | Security Consultant | [36 empty] | 0
DR | Discern/Rules | [36 empty] | 0
Core | Core Build Consultant | [36 empty] | 0
Alph | Alpha S/'W Engineer | [36 empty] | 0
Intf | Integration Engineer | [36 empty] | 0
| Subtotal Core FTEs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project X Impl Costs |  |  | 2004 |  |  |  |  | 2004 Jan Design: 2005 | [10 empty] | 2006
Role | Resources | Rate | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
PD | Partner/Project Director | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PE | Project Executive | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PA | Project Architect | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PA | Project Architect | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TPM | Technical PM | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SE | Systems Engineer | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TA | Technical Engineer | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AS | Application Specialist | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LC | Learning Consultant | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SC | Security Consultant | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DR | Discern/Rules | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Core | Core Build Consultant | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Alph | Alpha S/W Engineer | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Intf | Integration Engineer | 170 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Project Dollars |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fiscal Year 2004 Total | 0
| Fiscal Year 2005 Total | 0
| Fiscal Year 2006 Total | 0
| Fiscal Year 2007 Total | 0
| TOTAL | 0
Implementation
| Labor SUBTOTAL | 0
| Travel SUBTOTAL | 0 | 2004 Feb: CC01 travel estimate 20%
| Implementation Total | 0

## Contractor Labor
|  |  | 2004 | [10 empty] | 2005 | [11 empty] | 2006
Contactor Resources |  |  | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sept | Oct | Nov | Dec | Hours
Phase |  |  |  |  | Plan/Define | Plan/Define | Plan/Define | Design | Design | Design | Design | Design | Design | Design | Design | Build | Build | Build | Build | Test | Test | Test | Test | Pilot | Impl | Impl | Impl | Maintain | Maintain
C | Contract Project Manager | [36 empty] | 0
C | Contracted SMEs | [36 empty] | 0
C | Pace Temprorary Assistant | [36 empty] | 0
| Trainers | [36 empty] | 0
0
0
0
0
0
0
0
0
| Subtotal Core FTEs |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Costs |  |  | 2004 |  |  |  |  | 2005 Jan Design: 2005
Childrens Resources |  | FY04 Rate | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | [13 empty] | Cost
C | Contract Project Manager | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | Contracted SMEs | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
C | Pace Temprorary Assistant | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Trainers | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 11375 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
O |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
O |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
O |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
O |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
O |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
O |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Subtotal Core Project Dollars |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Fiscal Year 2004 Total | 0
| Fiscal Year 2005 Total | 0
| Fiscal Year 2006 Total | 0
| Fiscal Year 2007 Total | 0
| TOTAL | 0
Implementation
| Labor SUBTOTAL | 0
| Travel SUBTOTAL | 0
| Implementation Total | 0

## SW_HW_Maint
Vendor Software
| Software A | 0
| Software B | 0
| Software C | 0
| Tax on SW | 0
| Software SUBTOTAL | 0
| Software Discount | 0
| Software TOTAL | 0
Vendor Hardware
| Hardware A | 0
| Hardware B | 0
| Hardware C | 0
| Tax on HW | 0
| Hardware SUBTOTAL | 0
| Hardware Discount | 0
| Hardware TOTAL | 0
Vendor Maintenance
| Maintenance A | 0 | annual
| Maintenance B | 0 | annual
| Maintenance SUBTOTAL | 0
| Maintenance Discount | 0
| Maintenance TOTAL | 0
| Contract TOTAL | 0
Other Software
| Software A | 0
| Software B | 0
| Software SUBTOTAL | 0
| Software Discount | 0
| Tax | 0
| Software TOTAL | 0
Other Hardware
| Hardware A |  | Thomas covering
| Hardware B | 0
| Hardware C | 0
| Hardware SUBTOTAL | 0
| Tax | 0
| Hardware Discount | 0
| Hardware TOTAL | 0
Other Maintenance
| Maintenance A | 0
| Maintenance B | 0
| Maintenance SUBTOTAL | 0
| Maintenance Discount | 0
| Maintenance TOTAL | 0
Total Software |  | 0
Total Hardware |  | 0
Total Maintenance |  | 0
No. Fiscal Years |  | 3 | Note: If change this no., need to spread SW & HW for fiscal years across no. of years
|  | FY04 | FY05 | FY06 | FY07
| SW | 0 | 0 | 0 |  | 0
| HW | 0 | 0 | 0 |  | 0
| Total | 0 | 0 | 0 | 0 | 0