## Dashboard
{Facility Name} PORTFOLIO MANAGEMENT DASHBOARD
Strategic Objective |  | Program / Initiative | Owner | Start Date | Est. End Date | Overall Status | Timeline Status | Benefits Status | Risks / Issues Status | Resource / Budget Status
Develop New Business Models and Innovative Products and Services | 1 | Program / Initiative | Name | MM-YY | MM-YY | On-Track | At-Risk | On-Track | On-Track | At-Risk
| 2 | Program / Initiative | Name | MM-YY | MM-YY | On-Track | On-Track | On-Track | On-Track | On-Track
| 2a | Pharmacy Concierge | Ross / Muhart | 2012-05-12 | 2013-04-01 | On-Track | On-Track | At-Risk | On-Track | On-Track
| 2b | CMS Bundled Payments | Ross | 2012-10-01 | 2014-06-30 | On-Track | At-Risk | On-Track | At-Risk | On-Track
| 3 | Program / Initiative | Name | MM-YY | MM-YY | At-Risk | At-Risk | At-Risk | At-Risk | At-Risk
Create Clinically Integrated Delivery System and Launch Progressive Care Models | 4 | Program / Initiative | Name | MM-YY | MM-YY | On-Track | On-Track | On-Track | On-Track | On-Track
| 4a | Project / Workstream | Name | MM-YY | MM-YY | On-Track | On-Track | On-Track | On-Track | On-Track
| 4b | Project / Workstream | Name | MM-YY | MM-YY | On-Track | On-Track | On-Track | On-Track | On-Track
| 4c | Project / Workstream | Name | MM-YY | MM-YY | On-Track | On-Track | On-Track | On-Track | On-Track
| 4d | Project / Workstream | Name | MM-YY | MM-YY | On-Track | On-Track | On-Track | On-Track | On-Track
| 5 | Program / Initiative | Name | MM-YY | MM-YY | At-Risk | At-Risk | At-Risk | At-Risk | At-Risk
| 5a | Project / Workstream | Name | MM-YY | MM-YY | On-Track | On-Track | On-Track | On-Track | On-Track
| 5b | Project / Workstream | Name | MM-YY | MM-YY | At-Risk | At-Risk | At-Risk | At-Risk | At-Risk
| 5c | Project / Workstream | Name | MM-YY | MM-YY | On-Track | On-Track | On-Track | At-Risk | On-Track
| 6 | Program / Initiative | Name | MM-YY | MM-YY | Not Started | Not Started | Not Started | Not Started | Not Started
Enhance Value and Implement Cost Reduction | 7 | Program / Initiative | Name | MM-YY | MM-YY | At-Risk | At-Risk | At-Risk | On-Track | At-Risk
| 7a | Project / Workstream | Name | MM-YY | MM-YY | At-Risk | At-Risk | At-Risk | On-Track | At-Risk
| 6b | Pharmacy Antibiotic Stewardship - Ph 1 | Marks | 2012-02-12 | 2012-10-12 | Complete | Complete | Complete | Complete | Complete
| 7b | Project / Workstream | Name | MM-YY | MM-YY | On-Track | On-Track | On-Track | On-Track | On-Track
| 8 | Program / Initiative | Name | MM-YY | MM-YY | On-Track | On-Track | On-Track | On-Track | On-Track
| 8a | Project / Workstream | Name | MM-YY | MM-YY | On-Track | On-Track | On-Track | On-Track | On-Track
| 8b | Staffing Ph 1: Optimize Nursing | Fernandez | 2012-02-12 | 2012-11-12 | On-Track | On-Track | At-Risk | On-Track | On-Track
| 6c | Staffing Ph 2: IQS - MRH | Fernandez | 2012-05-01 | 2012-08-01 | Complete | Complete | On-Track | Complete | Complete
| 8c | Staffing Ph 3: RCT - MHW | Fernandez | 2012-09-01 | 2012-12-01 | On-Track | On-Track | On-Track | On-Track | On-Track
| 8d | Staffing Ph 4: RCT - MHM | Fernandez | 2013-01-09 | 2013-04-15 | On-Track | On-Track | On-Track | On-Track | On-Track
| 8e | Project / Workstream | Name | MM-YY | MM-YY | On-Track | On-Track | At-Risk | On-Track | On-Track
| 8f | Project / Workstream | Name | MM-YY | MM-YY | On-Track | At-Risk | On-Track | On-Track | On-Track
Utilize Advanced Technology | 9 | Program / Initiative | Name | MM-YY | MM-YY | On-Track | On-Track | On-Track | On-Track | On-Track
| 8a | HIM / CDMP | Vignau | 2012-02-01 | 2014-10-01 | On-Track | On-Track | On-Track | On-Track | At-Risk
| 9b | Finance | Bussell | 2012-02-01 | 2014-10-01 | On-Track | On-Track | On-Track | On-Track | On-Track
| 9c | Clinical Operations | Reynolds | 2012-02-01 | 2014-10-01 | On-Track | On-Track | On-Track | On-Track | On-Track
| 9d | Training | M. Weber / Luongo | 2012-02-01 | 2014-10-01 | On-Track | On-Track | On-Track | On-Track | On-Track
| 9e | IT | K. Ross / K. Hood/ M. Riesco | 2012-02-01 | 2014-10-01 | On-Track | On-Track | On-Track | On-Track | On-Track
| 9f | RCM | Boucher | 2012-02-01 | 2014-10-01 | On-Track | On-Track | On-Track | On-Track | On-Track
| 9g | Physician | Freling / Salceda-Cruz | 2012-02-01 | 2014-10-01 | On-Track | On-Track | On-Track | On-Track | On-Track
| 9h | MIH | Harswick | 2012-02-01 | 2014-10-01 | On-Track | On-Track | On-Track | On-Track | On-Track
| 9i | Project Management | Wendy Iravedra / Ken Ross | 2012-02-01 | 2014-10-01 | On-Track | On-Track | On-Track | On-Track | On-Track
| 10 | Program / Initiative | Name | MM-YY | MM-YY | On-Track | On-Track | On-Track | On-Track | On-Track
As of: {Date}

## Comments
Strategic Objective |  | Program / Initiative | Comments
Develop New Business Models and Innovative Products and Services | 2 | Asset Evaluation | On hold pending completion of budget reviews
| 3 | Innovative Products / Services
| 3a | Pharmacy Concierge | ~1038 scripts filled to date (71 last week). MTD capture rate of 3.5% versus 5% target (based on eligible insurance). Working on increasing demand at MRH and JDHC. Humana contract approved but awaiting config data to set up for payment. Site visits to MRHS and MHP completed. Developing plan for roll-out system-wide. Expect some delays with Medicaid qualification and insurance contract expansion. Plan to do South then Pembroke followed by Miramar and / or West
| 3b | CMS Bundled Payments | Care model redesign recommendations being finalized - expect 3/31; draft gain sharing model complete and under Legal review, physician participation agreement under development - expect both 3/15; scorecard metrics will be developed after care model is finalized, beneficiary communications pending CMS guidance; Premier requested EPMO present project governance structure and timeline at next cohort call
| 4 | Project Everglades | Still little movement on LMHS side. Executive update scheduled for ~4/1
Create Clinically Integrated Delivery System and Launch Progressive Care Models | 3 | Clinical Integration | Will be removed from Dashboard post March 28th Board meeting
| 3a | Operations | Operations manager offer made 3/1; Physician orientation sessions begin Thursday
| 3b | Credentialing and Peer Review | Dewveloping policies and procedures
| 3c | Finance and Contracting | Shared savings methodology slated for approval at March Board meeting; meeting last night to approve budget and begin discussing contracting strategy and targets (employer / payer)
| 3d | Quality and Information Technology | Meeting next week, working on finalizing benchmarks and baselines; 1st progress report to be issued in May
| 4 | Physician Alignment Strategies
| 4a | Primary Care | PCPs developing business plan and proposal with Holland and Knight to present to the District, Kim to follow up with Maria Currier to develop timeline; expect proposal to be complete by end of March; Braver – Wishes to re-engage on the acquisition of his Hollywood office – not Aventura location.
| 4b | Surgical Specialists | Surgeons: 3 contracts executed, 1 contract expected; 3 in DD, 1 in discussion; Ortho: no progress; ENT: 2 fully implemented, 1 in discussion for chief - site visit 3/12
| 4c | Medical Specialists | Cardiology: reps from 2 key groups meeting to define go-forward strategy (delayed due to vacations); Neuro: Dr. Shebert + 3 in discussions, pursuing recruitment, add'l 1 in discussion; OB/GYN: recruiting 2 - 3 under coillection guarantees; Pysiatry: contract delivered, pending response
| 4d | ED Coverage (Hospitalists & Specialists) | RFI expected to be issued 3/8; meeting with hospital CEOs today to finalize and review communications strategy / plan
Enhance Value and Implement Cost Reduction | 5 | Clinical Effectiveness
| 5a | VBP, Readmissions and LOS | Staffing requirements for rolling out strategies to AMI and PN have been determined (3.5 FTEs) and are being validated at the facility level for inclusion in budget, also defining KPIs and tracking process, will return to Executive Staff in late April with progress update, system level focus on transitional care and community partners as well as Epic enhancements (complaince with starndard order sets tracking / reporting, utilization of disease management module for CHF - 90% implemented)
| 5b | Pharmacy Antibiotic Stewardship | Criteria Based Order sets for top 4 high cost ,inappropriately used antibiotics being built into Epic and expected to be released in this month
| 6 | Cost Reduction
| 6a | Task Execution | Total reported savings to date is $46.7M vs. a $48.9M target. Complete (95.5%). Phase 2 still to be defined - target to be set based on AHCA comparison
| 6b | Staffing Ph 1: Optimize Nursing | MRH made adjustment totalling $234k since last pay period (60% increase); if accurate, have exceeded overall target: $5.1 million of target $4.9M through pay period ending 2/23/13; MHP 94%, MHR 70%, all others have exceeded target
| 6c | Staffing Ph 2: IQS - MRH | Reported $3 million implemented (some double counting) + $1.4 million planned at 90 day summation, complete, remove?
| 6d | Staffing Ph 3: RCT - MHW | Executed 43 of 64 opportunities for a realized benefit of ~$554k versus $714k target (78%)
| 6e | Staffing Ph 4: RCT - MHM | Data review complete for 20 of 25 departments, 30 day check in and lean tools workshop on Wednesday 3/6
| 6f | Revise HR Benefit - Phase 1 | 2012 baseline will be established in April and savings monitored quarterly in conjunction with MHN process
| 6f | Human Resources Reorganization | Some slippage in interim milestones dates: delays in posting / filling leadership positions (move from 4/1 to mid April / early May), alignment on which Employee Health functions will be centralized; EAP RFI - cillecting responses through 3/7; LOA RFP - reviewing responses 3/13, orals to be scheduled; process redesign timeline under development - initial focus on Tuition loan and reimbrsement; satisfactory reference check on Lawson - HR Global with Geisinger, working on development of implementation timing and resources (1 - 2 years with ~4 FTEs per initial estimates), will bring to ES
| 7 | ICD10
| 7a | HIM / CDMP | Looking to contract to hire for workstream lead, clinical documentation project at-risk for budget
| 7b | Finance
| 7c | Clinical Operations
| 7d | Training
| 7e | IT | Issue with 3M CAC Encoder failure resolved
Utilize Advanced Technology | 7f | RCM
| 7g | Physician
| 7h | MIH
| 7j | Project Management | Deloitte PM on-boarded and developing detailed workplan with workstream leads, EPMO PM support FT beginning in June (Abby)
| 8 | Epic
| 8a | EHR Ambulatory
| 8b | Epic Inpatient Clinicals (EIC) | EIC at MPH, MWH, UCC, Manor – Go live 4/20/2013; outpatient and cardiac rehab go live mid 2013
| 8b | Radiant and Cupid | Radiant and Cupid – Start 5/1/2013 , Target Go-Live 7/13/2014: All hospitals, Training analyst and pre-planning has already begun
| 8b | Upgrade to 2012 | Upgrade to 2012 – Start 6/1/2013, Target Go-Live Nov 2013: All hospitals
| 8c | Standardization of Order Sets | 616 standard order sets completely implemented
| 9 | EHR Donation Program | EHR- 130 practices signed with 220 providers. 36 practices interested with 71 providers. 96% of 230 goal by end of FY2013 HIE-26 practices LIVE with 35 providers and 139 named users; interface with Florida HIE go-live this week (17 organizations including Broward Health, Martin Health, Mt. Sinai Medical Center, Tampa Bay RHIO)

## Comments (hidden)
Strategic Objective |  | Program / Initiative | Comments
Develop New Business Models and Innovative Products and Services | 2 | Asset Evaluation | On hold pending completion of budget reviews
| 3 | Innovative Products / Services
| 3a | Pharmacy Concierge | ~880 scripts filled to date (76 last week). Humana requested add'l info. Cigna denied application for non-Mcre b/c not a retail pharmacy. Rolled out hospital wide at JDHC and MRH - working on increasing demand. 2.18% fill rate (versus target of 5%), sponsor mtg 2/28
| 3b | CMS Bundled Payments | Care model redesign recommendations presented 2/18; draft gain sharing model complete and under Legal review, physician participation agreement under development, comments provided on CMS Quality metrics and scorecard development underway, communications plan in under Lead / Sponsor review, beneficiary communications pending CMS guidance
| 4 | Project Everglades | Little movement on LMHS side.
Create Clinically Integrated Delivery System and Launch Progressive Care Models | 3 | Clinical Integration | Will be removed from Dashboard post March 28th Board meeting
| 3a | Operations | Operations manager interviews underway
| 3b | Credentialing and Peer Review | Approved physician orientation materials
| 3c | Finance and Contracting | Shared savings methodology approved by F&C, slated for approval at March Board meeting
| 3d | Quality and Information Technology | Scorecard approved
| 4 | Physician Alignment Strategies
| 4a | Primary Care | PCPs developing business plan and proposal with Holland and Knight to present to the District, Kim to follow up with Maria Currier to develop timeline; expect proposal to be complete by end of March
| 4b | Surgical Specialists | Surgeons: 4 in contracting, 2 in DD, 2 in discussion; Ortho: no progress; ENT: 2 fully implemented, 2 in discussion
| 4c | Medical Specialists | Cardiology: reps from 2 key groups meeting to define go-forward strategy; Neuro: Dr. Shebert + 4 in discussions, if unsuccessful, will pursue recruitment; OB/GYN: providing recruitment assistance; Pysiatry: DD being evaluated
| 4d | ED Coverage (Hospitalists & Specialists) | Proceeding towards closed hybrid model, proceeding with assessment of ED coverage contract, RFI to be issued 3/8
Enhance Value and Implement Cost Reduction | 5 | Clinical Effectiveness
| 5a | VBP, Readmissions and LOS | Team working on defining staffing requirements for rolling out strategies to additional diagnoses, also defining KPIs and tracking process, return to Executive Staff 3/8
| 5b | Pharmacy Antibiotic Stewardship | Phase 2 timeline complete, initial focus on Criteria Based Order sets for high cost ,inappropriately used antibiotics
| 6 | Cost Reduction
| 6a | Task Execution | Total reported savings to date is $46.7M vs. a $48.9M target. Complete (95.5%). Phase 2 still to be defined - target to be set based on AHCA comparison
| 6b | Staffing Ph 1: Optimize Nursing | Have achieved $4.6 million of target $4.9M through pay period ending 1/12/13; JDHC, MHM, MRHS have exceeded plan; MHW 94%, MHP 89%, MHR 43%
| 6c | Staffing Ph 2: IQS - MRH | Reported $3 million implemented (some double counting) + $1.4 million planned at 90 day summation, complete, remove?
| 6d | Staffing Ph 3: RCT - MHW | Monitoring of execution beginning this week, will report monthly
| 6e | Staffing Ph 4: RCT - MHM | Data collection and review underway
| 6f | Revise HR Benefit - Phase 1 | 2012 baseline will be established in April and savings monitored quarterly in conjunction with MHN process
| 6f | Human Resources Reorganization | Some slippage in interim milestones dates: posting leadership positions, alignment on which Employee Health functions will be centralized, selecting HRIS vendor (unsatisfactory ref check with Cleveland Clinic, follow up with Geisinger - site visit 2/26)
| 7 | ICD10
| 7a | HIM / CDMP | Looking to contract to hire for workstream lead, clinical documentation project at-risk for data, timeline and budget
| 7b | Finance
| 7c | Clinical Operations
| 7d | Training
| 7e | IT | Issue with 3M CAC Encoder failure. Solution in beta testing. Questions remain re: workstream lead allocation
| 7f | RCM
| 7g | Physician
| 7h | MIH
| 7j | Project Management | Reported as "at-risk" due to admin assistant resource
| 8 | Epic
| 8a | EHR Ambulatory
| 8b | Epic Inpatient Clinicals (EIC) | EIC at MPH, MWH, UCC, Manor – Go live 4/20/2013
| 8b | Radiant and Cupid | Radiant and Cupid – Start 5/1/2013 , Target Go-Live 7/13/2014: All hospitals, Training analyst and pre-planning has already begun
| 8b | Upgrade to 2012 | Upgrade to 2012 – Start 6/1/2013, Target Go-Live Nov 2013: All hospitals
| 8c | Standardization of Order Sets | 616 standard order sets completely implemented
| 9 | EHR Donation Program | EHR- 128 practices signed with 218 providers. 30 practices interested with 59 providers. 95% of 230 goal by end of FY2013 HIE-26 practices LIVE with 35 providers and 139 named users.